## Feature_Backlog
EdTech Platform — Feature Backlog (Course Project)
Hypothetical stakeholder sources: Students (n=120), Instructors (n=18), Administrators (n=6) ¦ Scoring: RICE + MoSCoW ¦ Target: +15 percentage points course completion (62% to 77%)
# | Feature / Initiative | Stakeholder Source | Category | Reach (users/qtr) | Impact (1–3) | Confidence % | Effort (weeks) | RICE Score | MoSCoW | Quarter
1 | Adaptive Quiz Engine | Students, Instructors | Learning Engine | 800 | 3 | 80 | 6 | 320 | Must Have | Q1
2 | Progress Dashboard | Students | Analytics | 950 | 3 | 90 | 4 | 641.25 | Must Have | Q1
3 | Mobile App — iOS & Android | Students | Platform | 1100 | 3 | 70 | 12 | 192.5 | Must Have | Q1
4 | Video Playback Speed Control | Students | UX/Platform | 900 | 2 | 95 | 2 | 855 | Must Have | Q1
5 | Instructor Analytics Portal | Instructors | Analytics | 180 | 3 | 85 | 5 | 91.8 | Must Have | Q2
6 | Gamification & Badges | Students | Engagement | 750 | 2 | 65 | 8 | 121.875 | Should Have | Q2
7 | Discussion Forums | Students | Community | 600 | 2 | 75 | 6 | 150 | Should Have | Q2
8 | Offline Mode | Students | Platform | 500 | 2 | 60 | 10 | 60 | Should Have | Q2
9 | AI Study Recommendations | Students | Learning Engine | 700 | 3 | 55 | 14 | 82.5 | Should Have | Q2
10 | Bulk Content Upload (Admin) | Administrators | Admin | 60 | 3 | 90 | 3 | 54 | Must Have | Q2
11 | LMS Integration (Canvas/Moodle) | Instructors, Admin | Integrations | 200 | 3 | 70 | 10 | 42 | Should Have | Q3
12 | Accessibility Mode (WCAG 2.1) | Students | Compliance | 1100 | 3 | 95 | 8 | 391.875 | Must Have | Q3
13 | Live Session Streaming | Instructors | Platform | 300 | 2 | 60 | 12 | 30 | Could Have | Q3
14 | Peer Review Assignments | Students, Instructors | Learning Engine | 450 | 2 | 65 | 7 | 83.5714 | Should Have | Q3
15 | Certificate Generation | Students | Compliance | 900 | 3 | 85 | 3 | 765 | Must Have | Q3
16 | Dark Mode UI | Students | UX/Platform | 800 | 1 | 80 | 2 | 320 | Could Have | Q3
17 | Parent/Guardian Portal | Administrators | Admin | 150 | 2 | 50 | 8 | 18.75 | Could Have | Q4
18 | Subscription Management | Administrators | Admin | 200 | 3 | 80 | 5 | 96 | Should Have | Q4
19 | API for 3rd-party Plugins | Instructors | Integrations | 100 | 2 | 45 | 14 | 6.4286 | Won't Have | Q4
20 | Multi-language Support | Students | Platform | 400 | 2 | 55 | 16 | 27.5 | Won't Have | Q4
21 | Custom Branding (White-label) | Administrators | Admin | 50 | 2 | 40 | 12 | 3.3333 | Won't Have | Q4
22 | Spaced Repetition Flashcards | Students | Learning Engine | 600 | 2 | 70 | 5 | 168 | Could Have | Q4
23 | Student Cohort Grouping | Instructors | Admin | 180 | 2 | 65 | 4 | 58.5 | Could Have | Q4
24 | Email Digest (Weekly Summary) | Students | Engagement | 900 | 1 | 80 | 2 | 360 | Could Have | Q4
25 | Proctoring Integration | Administrators | Compliance | 300 | 3 | 50 | 18 | 25 | Won't Have | Q4

## Product_Roadmap
EdTech Platform — 3-Quarter Product Roadmap (12 High-Priority Initiatives)
Q1 — Foundation (4 features)
Initiative | Category | Priority | Business Impact | Success Metric | Est. Effort
Adaptive Quiz Engine | Learning Engine | Must Have | +8% completion rate | Quiz pass rate ≥ 75%; CSAT ≥ 4.2 | 6 wks
Progress Dashboard | Analytics | Must Have | Reduce drop-off 12% | DAU viewing dashboard ≥ 30% | 4 wks
Mobile App — iOS & Android | Platform | Must Have | +22% mobile engagement | App store rating ≥ 4.0; D7 retention ≥ 55% | 12 wks
Video Playback Speed Control | UX/Platform | Must Have | Reduce support tickets 15% | Feature adoption ≥ 40% in 30 days | 2 wks
Q2 — Engagement (4 features)
Initiative | Category | Priority | Business Impact | Success Metric | Est. Effort
Instructor Analytics Portal | Analytics | Must Have | Instructor NPS +15 pts | Weekly active instructors ≥ 60% | 5 wks
Bulk Content Upload (Admin) | Admin | Must Have | Save 3 hrs/wk per admin | Upload success rate ≥ 99% | 3 wks
Gamification & Badges | Engagement | Should Have | +10% course completion | Badge earn rate ≥ 25% of users | 8 wks
Discussion Forums | Community | Should Have | +5% peer engagement | Posts per active user ≥ 2/month | 6 wks
Q3 — Scale & Compliance (4 features)
Initiative | Category | Priority | Business Impact | Success Metric | Est. Effort
Accessibility Mode (WCAG 2.1) | Compliance | Must Have | Full ADA compliance | WCAG 2.1 AA audit passed | 8 wks
Certificate Generation | Compliance | Must Have | +18% course completion | Cert issued within 24hrs; error rate < 0.1% | 3 wks
Peer Review Assignments | Learning Engine | Should Have | +7% engagement depth | Avg review quality score ≥ 3.5/5 | 7 wks
LMS Integration (Canvas/Moodle) | Integrations | Should Have | Expand B2B pipeline | Sync error rate < 0.5%; onboard ≥ 3 institutions | 10 wks

## RICE_MoSCoW_Scoring
RICE & MoSCoW Scoring Methodology
RICE Score = (Reach × Impact × Confidence%) ÷ Effort ¦ Higher score = higher priority
Feature | MoSCoW | Reach | Impact | Confidence | Effort | RICE Score | Rank
Adaptive Quiz Engine | Must Have | 800 | 3 | 80% | 6 | 320 | 4
Progress Dashboard | Must Have | 950 | 3 | 90% | 4 | 641.25 | 3
Certificate Generation | Must Have | 900 | 3 | 85% | 3 | 765 | 2
Video Speed Control | Must Have | 900 | 2 | 95% | 2 | 855 | 1
Mobile App | Must Have | 1100 | 3 | 70% | 12 | 192.5 | 5
Instructor Analytics | Must Have | 180 | 3 | 85% | 5 | 91.8 | 9
Gamification & Badges | Should Have | 750 | 2 | 65% | 8 | 121.875 | 8
Peer Review | Should Have | 450 | 2 | 65% | 7 | 83.5714 | 10
Discussion Forums | Should Have | 600 | 2 | 75% | 6 | 150 | 7
LMS Integration | Should Have | 200 | 3 | 70% | 10 | 42 | 11
Spaced Repetition | Could Have | 600 | 2 | 70% | 5 | 168 | 6
Live Streaming | Could Have | 300 | 2 | 60% | 12 | 30 | 12
Rank compares the 12 features on this sheet. Feature_Backlog scores all 25 items; the roadmap takes all 8 Must Haves plus 4 Should Haves.

## Success_Metrics
Success Metrics & Acceptance Criteria — Target: +15 Percentage Points Course Completion (62% to 77%)
Initiative | Primary KPI | Baseline | Target | Acceptance Criteria
Adaptive Quiz Engine | Course Completion Rate | 62% | 73% | Quiz pass rate ≥ 75%; CSAT ≥ 4.2; completion lift ≥ 8pp
Progress Dashboard | Daily Active Users | 28% | 40% | ≥ 30% of users viewing dashboard weekly
Mobile App | Mobile Session Share | 12% | 35% | D7 mobile retention ≥ 55%; app rating ≥ 4.0
Gamification | Avg Sessions/User/Month | 4.2 | 6.5 | Badge earn rate ≥ 25%; completion lift ≥ 10pp
Certificate Generation | Completion Rate | 62% | 77% | Certs issued <24hrs; error < 0.1%
Instructor Analytics | Instructor NPS | 32 | 47+ | Weekly active instructors ≥ 60%
Peer Review | Engagement Depth Score | 2.1 | 3.0 | Avg review quality ≥ 3.5/5
Accessibility | ADA Compliance | Partial | Full WCAG 2.1 AA | Audit pass; zero critical violations
LMS Integration | B2B Pipeline | 0 institutions | 3+ institutions | Sync error rate < 0.5%
Discussion Forums | Peer Interaction Rate | 8% | 15% | Posts per active user ≥ 2/month
OVERALL TARGET | Course Completion Rate | 62% | 77% (+15pp) | Aggregate lift across all 12 initiatives
All baselines and targets are hypothetical planning figures for an illustrative platform.